## Slide 1: Improving Patient Flow In Clinics Methodology and Progress - So Far
5/11/16: “Administrator” meeting
  Created ‘administrator perceived’ list of probable problem areas
  Plan:
    Collect problems as perceived by MD’s and PC’s working in clinics
      Herminia Hermogenese – MD perceived problems
      John Mahon – PC perceived problems
    Give lists to Mentis to create ‘Clinic Questionnaire’
    Mentis to Present ‘Clinic Questionnaire’ to committee in two weeks
5/24/16: MD perceived problems to Mentis
6/16/16: PC perceived problems to Mentis

## Slide 2
Minnie created word document
  Ask MDs to corroborate/ identify new problems
Filled out by 10 MDs

## Slide 3
Minnie collated Forms from 10 MDs
  50 problems identified by MDs
  Prevalence of problem
    How many MDs/prob
    Which Clinics/prob
I went over collated data with Minnie
  Good idea of problems as perceived by MDs
  Formed backbone of the “Clinic Questionnaire”

## Slide 4
No data from John Mahon
6/16/16 Tracy Cullen sent data
  I think this is summary of data from original 5/11/16 meeting
If true that PCs have problems that have not been identified then:
  Not evaluated by “Clinic Questionaire”
  No new interventions will be tried in Pilot
  Reduced chance of improving their working situation wrt. these issues
  (Can be given voice: - If PCs enter these issues in “OTHER” section of Clinic Questionnaire)

## Slide 5: Improving Patient Flow/Care In Clinics Methodology and Progress So Far
5/11/16: “Administrator” meeting
5/24/16: MD perceived problems to Mentis
6/16/16: PC perceived problems to Mentis
6/28/16: ‘Clinic Questionnaire’ completed by Mentis
7/7/16: Admin ‘Tweek’ meeting
  Show and revise Clinic Questionnaire
    Aim: Identify and Quantify Problems in real-time. Validate against Staff Perceptions of problems
    Quick/easy to fill out, but still be valid and comprehensive enough for data to be useful
  Choose dates for implementation
    1st week: Reason: Date:
    2nd week: Reason: Date:
  Choose sites for implementation (? Yaphank, WSC)
  How to get Questionnaire to staff
    ?Staff copy onto desktop from common server/memory stick ?? Staff give computer No to IT who place on Desktop
  How to train staff in best way to fill out Questionnaire
Pre-Pilot Questionnaire Completion in Real-Time, over two weeks in Pilot-Clinics, by MDs and PCs
Pre-Pilot Questionnaire Analysis (Mentis)
Formulation of Pilot Interventions based on results of analysis (Mentis)
‘Pilot Interventions’ Meeting – finalize:
  What interventions to implement
  How to make implementations
  How long implementation need to be in place for any benefit to be seen
Implement Pilot – Institute changes into chosen clinics for chosen amount of time
Post-Pilot Questionnaire Completion (after implementation ) AT ALL CLINICS not just Pilot sites
Analyze Pre- and Post-Pilot Questionnaires’ (Mentis)
Pilot Results Meeting - Present Results of Pilot Interventions
  If Statistically Significant Improvement found:
    How to present this information To Albany to get whatever is necessary to IMPROVE PATIENT FLOW/CARE IN CLINICS